## Feuil1
Identifier | Document | Page/Paragraph | Classification | Comment | Answer | Status | Action (Y/N) | Action | Due date | Recom
JCD-01 | RPW-MEB-LFR-00003 | REQ-RPW-LFR-4706 | Major | The timing of the sequence composed of the 5 signals is not provided (duration of each signal). | The signal is changed for each snapshot. | Closed with action | Y | (LPP) Requirement REQ-RPW-LFR-4706 to be precised. A test Tests with different snapshot periods shall ne done. | 2019-06-01
JCD-02 | RPW-MEB-LFR-00003 |  | Major | There are many TBC remaining in this document. This should not be the case for QR. | The TBC/TBD can now be solved. | Closed with action | Y | (LPP) Solve the TBC/TBD in the document RPW-MEB-LFR-00003. | 2019-06-01
JCD-03 | RPW-MEB-LFR-SDD-00039 |  | Major | All the RAM is scrubbed. Do you initialize all the RAM at startup? What is done in case of double RAM error? Is this RAM subject to multiple stuck bits? | All the RAM is scrubbed (not just the area use by the OBSW). In case of double RAM error, a trap is executed. In addition to the SW scrubbing there is an HW scrubbing. The behaviour of the HW scrubbing should be verified. | Closed with action | Y | (LPP) Verify the behaviour of the SW AND HW scrubbing in case of multiple RAM errors. Verify that, in case of multiple stuck bits, it is possible to implement a SW workaround to recover the mission. | 2019-03-01
JCD-04 |  |  |  | The datapackage contains FPGA and IP core parts that are out of scope of this SW milestone. To be reviewed by HW experts. | The CNES project will verify that FPGA experts have already analysed this documentation. | Closed | N
JCD-05 | RPW-MEB-LFR-CDL-00037 |  | Major | Did you verify that all LEON3 Tech Notes related to HW problems have been taken into account? Where is documented this analysis? | Analysis to be done DAS analysis given for example | Closed with action | Y | (LPP) As it has been done for DAS by LESIA (see the example provided), make an analysis of the Tech Notes related to HW problems. | 2019-06-01
JCD-06 | RPW-MEB-LFR-RPT-00199-LPP-01-04 |  | Major | LFR Long tests seems not executed for the 3.2.0.24 version. Could you justify why it is not necessary? | The long term test will be executed | Closed with action | Y | (LPP) Execute the LFR long term test. | 2019-06-01
JCD-07 |  |  |  | The LFR SW technical budget (SW timing and sizing budget) are not found. Can you provide this document? | The SDD contains the technical budget. Regarding LFR. CPU and memory usages are < 70%. | Closed | N
CDN-01 | GENERAL |  | Minor | Many documents need to be signed or approved. Examples: - LPP IP User Manual - RPW Instrument LFR Software User Manual - SO-TR-RPW-SC-0277-LPC2E Updated onboard cal test report V10 - SPAMR, - etc. Could you please do a general verification ? | To be verified | Closed with action | Y | (LPP) Verify the each SW document contains at least one signature. | 2019-06-01
CDN-02 | RPW-MEB-LFR-QAD-00036_1.4_SPAMR | p14. / 5.6 | Minor | It is R3.2 milestone instead of R3++ | To be clarified | Closed with action | Y | (LPP) Clarify the SPAMR accordingly | 2019-06-01
CDN-03 | RPW-MEB-LFR-QAD-00036_1.4_SPAMR | p23 / 8.6 | Minor | - in SPAMR : 13 tests are "strictly V3.2 TESTS CASEs. - in SVR: 13 tests cases are strictly V3++. - In"RPW-MEB-LFR-CVM-00214-LPP-03-03_SSS-SRS-SVS-compliance_matrix_LFR_V3", column G (version), there is no version 3.2. Could you clarify ? Is there new test between V3++ and V3.2 ? | To be clarified | Closed with action | Y | (LPP) Precise in the SPAMR that all the tests were executed with version 3.2.0.24 of the software and that a new test was defined for this last version. | 2019-06-01
CDN-04 | RPW-MEB-LFR-CDL-00037_1.8-SCF | P6 / 6. | Minor | Information about compilation are on "https://hephaistos.lpp.polytechnique.fr/redmine/projects/lfr-fsw/wiki" is it possible to provide an extract in current datapack ? | Not efficient to duplicate this information. | Closed | N
CDN-05 | RPW-MEB-LFR-CDL-00037_1.8-SCF | general | Minor | Could you provide files that have been modified for this version ? | A code diff will be integrated in the SCF. | Closed with action | Y | (LPP) Integrate a code diff in the SCF. | 2019-06-01
CDN-06 | RPW-MEB-LFR-CDL-00037_1.8-SCF | P7 / 8.1 | Minor | There are 2 NCRs: Are you going to provide a new version ? | These NCR are not formally closed but they don't necessitate correction. | Closed
CDN-07 | RPW-MEB-LFR-CDL-00037_1.8-SCF | p8 / 4.1 | Minor | Previous SCF reference to update. | Typo to be corrected | Closed with action | Y | (LPP) Typo to be corrected | 2019-06-01
CDN-08 | RPW-MEB-LFR-CDL-00037_1.8-SCF | general | Minor | Please clarify what are: - V3++ - V3.2 - V3.2.0.24 - V3.2.0.15 versions. | 3++ and 3.2 are versions of datapackage. The latest version of the software is 3.2.0.24. | Closed
JCD-09 | RPW-SYS-MEB-DPS-CDL-001860-LES |  | Minor | In the DAS SCF, there is no reference to the correction of RPWMEB-599 (EM2) and or RPWMEB-671 (PFM @ 60°C). | SCF to be completed | Closed with action | Y | (LPP) SCF to be completed accordingly | 2019-06-01
JCD-10 | RPW-SYS-MEB-DPS-CDL-001860-LES |  | Major | The compilation options are not provided. Did you verify that all LEON3 Tech Notes related to HW problems have been taken into account? Where is documented this analysis? | Document provided. | Closed
JCD-11 | RPW-SYS-MEB-DPS-CDL-001860-LES |  | Major | What is the status of the 2 DAS RFD/RFW? | These RFD are closed | Closed
JCD-12 | RPW-SYS-MEB-DPS-PRC-000612-LES |  | Major | After §4.3, a paragraph explaining the delta validation of DAS 3.6.1.0 should be expected. | See integration tests | Closed
JCD-13 | RPW-SYS-MEB-DPS-PRC-000529-LES |  | Major | The SVS should be updated to include the new tests defined for the DAS 3.6.1.0. | See integration tests | Closed
CDN-09 | RPW-SYS-MEB-DPS-QAD-000280-LES_03.04_SPAMR | p15 / 3.9 | Minor | Explanation to clarify: code covered at 51,49% instead of 60%. | RFD already provided and agreed on this subject. | Closed
CDN-10 | RPW-SYS-MEB-DPS-CDL-001860-LES_01_00_SCF_RPW_DAS_R3++ | general | Minor | Could you provide files that have been modified for this version ? | A code diff will be integrated in the SCF. | Closed with action | Y | (LESIA) Integrate a code diff in the SCF. | 2019-06-01